## Summary
Metric | Value
Total Actions | 16
Completed | 0
In Progress | 0
Not Started | 16
Completion % | 0.0%
By Priority:
CRITICAL | 3
HIGH | 6
MEDIUM | 7
By Phase:
Immediate (0-7 days) | 5
Short-term (8-30 days) | 5
Medium-term (31-90 days) | 5
Long-term (91-365 days) | 1
Total Estimated Hours | 294
Average Hours per Action | 18.4

## Action Tracker
Action # | Action | Priority | Owner | Start Date | Due Date | Status | Deliverable | Dependencies | Estimated Hours | Notes
1 | Emergency Portfolio Triage | CRITICAL | Executive Director + Board | 2025-10-31 | 2025-11-06 | Not Started | Portfolio Triage Report with GO/NO-GO decisions | None | 12 | Convene emergency meeting, assess capacity, decide on each MOU
2 | CiF Project Recovery Plan | CRITICAL | Project Manager | 2025-10-31 | 2025-11-06 | Not Started | CiF Recovery Plan approved by CiF | Action 1 | 16 | Contact CiF within 24 hrs, propose scope reduction OR timeline extension
3 | Shelter Yetu Budget Disclosure | CRITICAL | Executive Director | 2025-10-31 | 2025-11-04 | Not Started | Budget disclosed and documented | None | 8 | Send demand email within 24 hrs, suspend if no response by deadline
4 | CAFO Event Feasibility Assessment | HIGH | CAFO Project Lead | 2025-11-02 | 2025-11-08 | Not Started | Event budget and GO/NO-GO recommendation | Action 1 | 8 | Calculate true cost, explore co-funding options
5 | Portfolio Financial Dashboard Creation | HIGH | Finance Manager or Executive Director | 2025-11-03 | 2025-11-10 | Not Started | Live dashboard tracking all MOUs | Action 1, 3 | 12 | Create 5-sheet spreadsheet: Portfolio Summary, Cashflow, Staff Allocation, Deliverables, Risks
6 | Formalize VCE Governance Structure | HIGH | Executive Director + Board | 2025-11-10 | 2025-11-30 | Not Started | Board establishment docs OR Board meeting minutes | Action 1 | 20 | CAFO grant requires active Board of Directors - confirm or establish
7 | Suspend ADRA & TFC Governance Activities | MEDIUM | Executive Director | 2025-11-11 | 2025-11-15 | Not Started | Suspension notices sent and acknowledged | Action 1 | 4 | Free up 10 hrs/month staff time for active projects
8 | Develop Standard Project Management Templates | MEDIUM | Project Manager or Operations Lead | 2025-11-11 | 2025-11-30 | Not Started | Template library (6 templates) + staff training | None | 24 | Charter, WBS, Risk Register, Status Report, Financial Report, Closeout templates
9 | Establish Weekly Portfolio Standup | MEDIUM | Executive Director or Portfolio Manager | 2025-11-11 | 2025-11-11 | Not Started | Weekly meeting cadence established | Action 1 | 4 | Every Monday 9-10am, all staff, mandatory attendance (1 hr/week ongoing)
10 | Negotiate CiF Milestone Payment Clarity | HIGH | Finance Manager + Executive Director | 2025-11-08 | 2025-11-15 | Not Started | Written milestone payment agreement from CiF | Action 2 | 6 | Clarify $10,200 split across 3 undefined milestones
11 | Develop VCE Resource Capacity Model | MEDIUM | Executive Director + HR | 2025-12-01 | 2026-01-31 | Not Started | VCE Resource Capacity Model (Excel tool) | Action 5 | 16 | Define max concurrent project load based on actual staff capacity
12 | Address Shelter Yetu Dual-Role Conflict | HIGH | Executive Director + VCE Board | 2025-11-15 | 2025-12-31 | Not Started | Internal controls memo + future policy | Action 3, 6 | 12 | Short-term: independent oversight. Long-term: decline dual-role arrangements
13 | Conduct MOU Portfolio Lessons Learned | MEDIUM | Executive Director with all staff | 2026-01-02 | 2026-01-31 | Not Started | Lessons Learned Report + Best Practices Guide | CiF, CAFO, Shelter projects completed | 16 | Conduct after all 2025 projects close out
14 | Develop Financial Sustainability Strategy | HIGH | Executive Director + Board + Finance Manager | 2026-01-01 | 2026-02-28 | Not Started | Financial Sustainability Strategy document | Action 11, 13 | 32 | True cost analysis, pricing strategy, reserve building, project selection criteria
15 | Renegotiate or Exit Non-Performing MOUs | MEDIUM | Executive Director | 2026-01-15 | 2026-03-31 | Not Started | MOU Portfolio Review Report + renewed/amended/terminated MOUs | Action 13, 14 | 24 | Assess each MOU: CiF, CAFO, Shelter, TFC, ADRA - renew, renegotiate, or exit
16 | Institutionalize Portfolio Management Practices | MEDIUM | Executive Director | 2026-04-01 | 2026-10-31 | Not Started | Portfolio Management Framework + PMO operational | Actions 8, 11, 14 | 80 | Establish PMO, standardize project lifecycle, gated approvals, portfolio governance rhythm

## Milestones
Milestone | Target Date | Status | Dependent Actions | Success Criteria
Emergency Triage Complete | 2025-11-06 | Not Started | 1, 2, 3, 4 | GO/NO-GO decisions made for all 5 MOUs
Q4 2025 Deliverables Managed | 2025-11-30 | Not Started | 5, 9, 10 | CiF, CAFO, Shelter projects on track or renegotiated
Governance Formalized | 2025-11-30 | Not Started | 6, 7 | Board operational, ADRA/TFC governance suspended
Project Management Infrastructure | 2025-11-30 | Not Started | 8, 9 | Templates in use, weekly standups established
2025 Projects Closed | 2025-12-31 | Not Started | 2, 4 (CiF, CAFO complete) | All deliverables submitted, final reports delivered
Capacity & Sustainability Defined | 2026-02-28 | Not Started | 11, 13, 14 | Capacity model, sustainability strategy, lessons learned complete
Portfolio Rationalized | 2026-03-31 | Not Started | 15 | MOUs renewed/renegotiated/exited based on performance
Portfolio Management Maturity | 2026-10-31 | Not Started | 16 | PMO operational, standardized processes, sustainable operations

## Weekly Checklist
Week | Dates | Actions Due This Week | Status | Notes
Week 1 | Oct 30 - Nov 05, 2025 | Action 3: Shelter Yetu Budget Disclosure | Not Started
Week 2 | Nov 06 - Nov 12, 2025 | Action 1: Emergency Portfolio Triage; Action 2: CiF Project Recovery Plan; Action 4: CAFO Event Feasibility Assessment; Action 5: Portfolio Financial Dashboard Creation; Action 9: Establish Weekly Portfolio Standup | Not Started
Week 3 | Nov 13 - Nov 19, 2025 | Action 7: Suspend ADRA & TFC Governance Activities; Action 10: Negotiate CiF Milestone Payment Clarity | Not Started
Week 4 | Nov 20 - Nov 26, 2025 | None | Not Started
Week 5 | Nov 27 - Dec 03, 2025 | Action 6: Formalize VCE Governance Structure; Action 8: Develop Standard Project Management Templates | Not Started
Week 6 | Dec 04 - Dec 10, 2025 | None | Not Started
Week 7 | Dec 11 - Dec 17, 2025 | None | Not Started
Week 8 | Dec 18 - Dec 24, 2025 | None | Not Started

## Instructions
Section | Instructions
OVERVIEW | This workbook tracks the 16-action improvement plan for VCE MOU portfolio.
HOW TO USE THIS TRACKER | 1. Review Summary sheet to understand overall progress 2. Use Action Tracker as main working sheet 3. Check Milestones to track major achievements 4. Use Weekly Checklist for short-term focus 5. Update weekly during Portfolio Standup meeting
SUMMARY SHEET | High-level view of portfolio improvement progress. Review monthly with Board.
ACTION TRACKER SHEET | Main working sheet. Update Status for each action: - Not Started: No work begun - In Progress: Work underway - Complete: Deliverable finished Add completion dates and notes as you go.
MILESTONES SHEET | Eight major milestones marking significant progress. Used for Board reporting and partner communications.
WEEKLY CHECKLIST SHEET | Week-by-week focus for first 8 weeks (immediate + short-term actions). Review every Monday in standup meeting.
UPDATING | CRITICAL: Update this tracker WEEKLY, ideally during Monday standup meeting. Assign one person as Tracker Owner responsible for updates.
COLOR CODING | Consider using conditional formatting: - RED: Overdue actions - YELLOW: Actions due within 7 days - GREEN: Completed actions - BLUE: Future actions (due >7 days out)
ESCALATION | IF action is >7 days overdue: 1. Discuss blocker in standup 2. Escalate to Executive Director 3. Document reason for delay in Notes 4. Update Due Date if rescheduled (with ED approval)